Schedule

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Date | Task | Outcome | Responsible teacher(s)/adult(s) | Student(s) | Comments |
| 2012 November | choose participating students |  |  |  |  |
| 2012 December | start working on the Comenius website |  |  |  |  |
| 2012 December | translating Hungarian folksongs into English |  |  |  |  |
| 2012 December | preparing Christmas cards | Christmas cards to be sent to the partner schools |  |  |  |
| 2012 December – 2013 January | creating logos for the whole Comenius project | logos |  |  |  |
| 2012 December – 2013 January | finishing and uploading things on the Comenius website | Comenius website (comenius.bgrg.hu) |  |  |  |
| 2012 December – 2013 January | making sheet music and drawings to the song booklet | song booklet |  |  |  |
| 2013 January | preparing a CD with folk songs, sung by participating students | CD |  |  | studio quality if possible |
| 2013 January – February | preparing and learning dances and finding music | CD and choreographies |  |  | costumes? |
| 2013 February | exhibiting and choosing the best logo | one logo to be taken to the next meeting |  |  |  |
| 2013 February 23 – March 1 | meeting in the Czech Republic | presentations of songs and dances and sharing the booklets and CDs with each other |  |  |  |